Estimate TOTAL = $2,299,430 (service cost) + $1,200 (material cost) = $2,300,630

| Final Month – |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Months 6-11 – Maintain 15 clients |  |  |  |  |  |  |  |  |  |  |  |  |
| Months 3-5 – Build to maximum of 15 clients starting 3 new per month |  |  |  |  |  |  |  |  |  |  |  |  |
| Months 1-2 – Start with 4 clients in phase 2, start 3 new clients per month. |  |  |  |  |  |  |  |  |  |  |  |  |
| Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| BCBA 6 hours wk for all clients in phase 2 | 4 Clients in phase 2 = 4*6hrs = 24hrs BCBA weekly 24*$114.75 = $2,754 wk Total Month 1 for BCBA hrs $11,016 | 7 Clients in phase 2 = 7*6hrs = 42hrs BCBA weekly 42*$114.75 = $4819.50 wk Total Month 2 for BCBA hrs $19,278 | 10Clients in phase 2 = 10*6hrs = 60hrs BCBA weekly 60*$114.75 = $6885 wk Total Month 2 for BCBA hrs $27, 540 | 13 Clients in phase 2 = 13*6hrs = 78hrs BCBA weekly 78*$114.75 = $8950 wk Total Month 2 for BCBA hrs $35, 802 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 | 15Clients in phase 2 = 15*6hrs = 90hrs BCBA weekly 90*$114.75 = $10,327 wk Total Month 2 for BCBA hrs $41,310 |
| BCBA-D Fifteen (15) hours max wk for all clients in Phase 1. Six (6) hours max wk for clients in phase 2 | 4 Clients in phase 2 = 4*6hrs= 24hrs BCBA-D weekly 24*$140.25 = $3,366 wk $13,464 mth 3 NEW clients in Phase 1 = 3*15hrs = 45 hrs weekly 45*$140.25= $6,311.25 wk $6,311.25*4= $25,245 mth GRAND TOTAL $36,261 | 7 Clients in phase 2 = 7*6hrs= 42hrs BCBA-D weekly 42*$140.25 = $5809.5 wk $23,562 mth 3 NEW clients in Phase 1 = 3*15hrs = 45 hrs weekly 45*$140.25= $6,311.25 GRAND TOTAL $49,151.25 | 10 Clients in phase 2 = 10*6hrs= 60hrs BCBA-D weekly *$140.25 = $8415 wk $33,660 mth 3 NEW clients in Phase 1 = 3*15hrs = 45 hrs weekly 45*$140.25= $6,311.25 GRAND TOTAL 67, 511 | 13 Clients in phase 2 = 13*6hrs= 78hrs BCBA-D weekly 78*$140.25 = $10,939.50 wk $43,758 mth 2 NEW clients in Phase 1 = 2*15hrs = 30 hrs weekly 30*$140.25= $4,207.50 GRAND TOTAL $83,767.50 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 | 15 Clients in phase 2 = 15*6hrs= 90hrs BCBA-D weekly 90*$140.25 = $12,622.50 wk $50,490 mth 0 NEW clients in Phase 1 = 0*15hrs = 0 hrs weekly $0 GRAND TOTAL $91,800 |